## Project Management Data
Excel Sample Data
Project Management Data | [6 empty] | project types | Proj_cent%_progress | Proj_Less20%_progress | Proj_50%_progress | Total_task_per_project
[7 empty] | Marketing | 1 | 1 | 0 | 4
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress | Product Dev | 1 | 1 | 0 | 3
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78% | Customer Svc | 2 | 1 | 0 | 3
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100% | Financial | 1 | 1 | 0 | 3
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45% | Research | 0 | 2 | 1 | 3
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0% | Development | 1 | 2 | 0 | 3
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100% | Production | 0 | 2 | 0 | 3
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78% | Sales | 0 | 1 | 0 | 3
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0% | Support | 2 | 1 | 0 | 3
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100% | Operations | 0 | 2 | 0 | 3
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100% | Consulting | 0 | 2 | 0 | 3
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0% | Training | 0 | 2 | 0 | 3
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10% | Events | 0 | 2 | 0 | 3
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78% | Logistics | 1 | 1 | 1 | 3
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100% | Engineering | 0 | 3 | 0 | 3
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100% |  | Total_employees | Person_per_project | COUNT_OF_HOLDING_PROJECTS
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0% |  | Alice | Marketing | 1
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0% |  | Bob | Marketing | 1
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30% |  | Charlie | Marketing | 1
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0% |  | Daisy | Marketing | 1
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0% |  | Ethan | Product Dev | 1 |  | Those who hold 2 projects each
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70% |  | Fiona | Product Dev | 2 |  | Fiona
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78% |  | Gabriel | Product Dev | 1 |  | Mark
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0% |  | Hannah | Customer Svc | 1 |  | Quinn
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100% |  | Ian | Customer Svc | 1 |  | Rachel
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100% |  | Julia | Customer Svc | 1
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0% |  | Kevin | Financial | 1
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40% |  | Mark | Financial | 2
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0% |  | Nathan | Research | 1
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0% |  | Olivia | Research | 1
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60% |  | Peter | Research | 1
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0% |  | Quinn | Development | 1
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0% |  | Rachel | Development | 2
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80% |  | Sam | Development | 2
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0% |  | Tim | Production | 1
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0% |  | Ursula | Production | 1
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30% |  | Victor | Production | 1
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0% |  | Wendy | Sales | 1
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0% |  | Xavier | Sales | 1
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50% |  | Yvette | Sales | 1
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100% |  | Zoe | Support | 1
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0% |  | Aaron | Support | 1
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20% |  | Bella | Support | 1
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0% |  | Calvin | Operations | 1
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0% |  | Diane | Operations | 1
[8 empty] | Edward | Operations | 1
[8 empty] | Gary | Consulting | 1
[8 empty] | Helen | Consulting | 1
[8 empty] | Isaac | Training | 1
[8 empty] | Jane | Training | 1
[8 empty] | Kyle | Training | 1
[8 empty] | Laura | Events | 1
[8 empty] | Mike | Events | 1
[8 empty] | n Nancy | Events | 1
[8 empty] | Oscar | Logistics | 1
[8 empty] | Patricia | Logistics | 1
[8 empty] | Quentin | Logistics | 1
[8 empty] | Tom | Engineering | 1